## CommentRelpy Sheet
NISOC |  | Development Plan of 28 Reservoirs / BIBI HAKIMEH Oilfield
Contract No.: 053-073-9189 |  | Comment / Reply Sheet |  |  |  |  | Page 1 of 1
Ref. Transmittal No: BH-GS-MS-VT-0019 |  |  |  |  | Ref. Transmittal Date: | 1403/07/22 | Project No.: 971022
Comment Sheet No.: VD-BH-0019-01162 |  |  |  | Date:1403/08/01 | Comment Reply Sheet No.: Reply Sheet -GSS-007 |  | Date: | 1403/12/18
Document No.: VD-BH-00-GS-000-PI-LI-0014 |  | Document Title: Recommended spare part list for commissioning |  |  |  | Rev.: 00 | Comment Status: Commented
*- Comment Status: |  |  |  |  | Clarification Status:
CO – Commented |  |  | AFC – Approved For Construction |  | C– Close (Comment Be Implemented Immediately) O –Open (Need action) H – Hold
NC – No Comment |  |  | AFD – Approved For Design
AN – Approved As Noted |  |  | AFP – Approved For Procurement
AP – Approved |  |  | RJ – Rejected
No. | CLIENT Comments |  |  |  | Contractor Clarification |  |  |  | Clarification Status
1 | spare part quantities are incorrect. according to pre-com and spare part procedure (E&C-QC-SP-1, clause 1.7)attached, numbers including decimals must be rounded up. please consider and revise quantities. |  |  |  | Spare parts quantity revised according to the latest approved spare part list
2 | please add item codes and piping class to the document. |  |  |  | Noted
3 | Please add Daryapala logo to all pages. |  |  |  | Noted
4
5
Comments by : |  |  |  |  | Clarified by :