## COVER_SHEET
Vendor Print Index and Schedule
Rev. | Date | Purpose Of Issue | Prepared | Checked | Approved | Client Approval
00 | 12.04.2025 | Issued for Comment | Y.Navasartian | S.Morid | S.Morid | -
Class: A
Status: | IFC: Issued For Comment
IFI: Issued For Information
IFA: Issued For Approval
AB-R: As-Built for COMPANY Review
FI: Final Issue
AB-A: As-Built –Approved
Vendor Print Index and Schedule
Development Plan of 28 Reservoirs
/ BIBI HAKIMEH Oilfield (EPC)
Type
Project Code
Sequence No.
Rev.
Page No. : 1 of 3
Work Package
Discipline
Project No.:
CLIENT:
CONTRACTOR:
NISOC
51-53-971022
Conteacror
Facility
Vendor Document
BH
00
IN
VL
1001
00
PQ
000
VD

## Rev_His
Tabulation of Revised Pages
| SHEET | REVISIONS |  |  | SHEET |  | REVISIONS
|  | 00 | 01 | 02 |  |  | 00 | 01 | 02
| 1 | X |  |  | 51
| 2 | X |  |  | 52 | 52
| 3 | X |  |  | 53 | 53
| 4 |  |  |  | 54 | 54
| 5 |  |  |  | 55 | 55
| 6 |  |  |  | 56 | 56
| 7 |  |  |  | 57 | 57
| 8 |  |  |  | 58 | 58
| 9 |  |  |  | 59 | 59
| 10 |  |  |  | 60 | 60
| 11 |  |  |  | 61 | 61
| 12 |  |  |  | 62 | 62
| 13 |  |  |  | 63 | 63
| 14 |  |  |  | 64 | 64
| 15 |  |  |  | 65 | 65
| 16 |  |  |  | 66 | 66
| 17 |  |  |  | 67 | 67
| 18 |  |  |  | 68 | 68
| 19 |  |  |  | 69 | 69
| 20 |  |  |  | 70 | 70
| 21 |  |  |  | 71 | 71
| 22 |  |  |  | 72 | 72
| 23 |  |  |  | 73 | 73
| 24 |  |  |  | 74 | 74
| 25 |  |  |  | 75 | 75
| 26 |  |  |  | 76 | 76
| 27 |  |  |  | 77 | 77
| 28 |  |  |  | 78 | 78
| 29 |  |  |  | 79 | 79
| 30 |  |  |  | 80 | 80
| 31 |  |  |  | 81 | 81
| 32 |  |  |  | 82 | 82
| 33 |  |  |  | 83 | 83
| 34 |  |  |  | 84 | 84
| 35 |  |  |  | 85 | 85
| 36 |  |  |  | 86 | 86
| 37 |  |  |  | 87 | 87
| 38 |  |  |  | 88 | 88
| 39 |  |  |  | 89 | 89
| 40 |  |  |  | 90 | 90
| 41 |  |  |  | 91 | 91
| 42 |  |  |  | 92 | 92
| 43 |  |  |  | 93 | 93
| 44 |  |  |  | 94 | 94
| 45 |  |  |  | 95 | 95
| 46 |  |  |  | 96 | 96
| 47 |  |  |  | 97 | 97
| 48 |  |  |  | 98 | 98
| 49 |  |  |  | 99 | 99
| 50 |  |  |  | 100 | 100
Vendor Print Index and Schedule
Development Plan of 28 Reservoirs
/ BIBI HAKIMEH Oilfield (EPC)
Type
Project
Sequence No.
Rev .
Page No. : 2 of 3
Work Package
Discipline
Project No.:
CLIENT:
CONTRACTOR:
NISOC
51-53-971022
Conteacror
Facility
Vendor
BH
00
IN
VL
1001
00
CONTRACTOR:
PQ
000
VD

## A4 LANSCAPE
|  | Vendor Print Index and Schedule | [14 empty] | PURCHASER
VENDOR
DOC NO. |  | VD-BH-00-PQ-000-IN-VL-1001 |  | REQUISITION NO. : BH-17-SM-000-IN-MR-1137-D00/BH-17-SM-000-IN-MR-0468-D00/BH-17-SM-000-IN-MR-2018-D00 | [12 empty] | LEGEND OF REVIEW CODE
PJT NAME |  | Development Plan of 28 Reservoirs / BIBI HAKIMEH Oilfield (EPC) |  | ISSUE DATE 12.04.2025 | [12 empty] | IFA : ISSUED FOR APPROVAL | [7 empty] | POI
P/O NO. : |  | 51-53-971022 |  | JOB NO. | [12 empty] | IFR : ISSUED FOR REVIEW
TAG NO. |  |  |  | MODEL NO. | [12 empty] | IFI : ISSUED FOR INFORMATION | [7 empty] | PURPOSE OF ISSUE
Item | DOC. NO. |  | DOCUMENT TITLE |  | CLASS | POI (MSA) | POI (NISOC) | Type | Weight | Quantity progress | W*Q | FORECAST DATE | REV.0 |  | REV.1 |  | REV.2 |  | REV.3 |  | REV.4 |  | REV.5 |  | REV.6
[13 empty] | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW | VENDOR | REVIEW
[13 empty] | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE | PURCHASER | CODE
General Documents: | [27 empty] | 22.5
1 | VD-BH-00-PQ-000-IN-VL-1001 |  | Vendor Print Index and Schedule |  | A | IFA | IFA | VL | [18 empty] | 4.6667 | 3
2 | VD-BH-00-PQ-000-IN-SH-1002 |  | Project Time Schedule |  | A | IFA | IFI | SH | [18 empty] | 3.1111 | 2
3 | VD-BH-00-PQ-000-IN-PR-1003 |  | Painting procedure |  | A | IFA | IFI | PR | [18 empty] | 3.1111 | 2
4 | VD-BH-00-PQ-000-IN-LI-1004 |  | Sub-vendor List |  | A | IFA | IFI | LI | [18 empty] | 0.77778 | 0.5
5 | VD-BH-00-PQ-000-IN-PR-1005 |  | Factory Acceptance Test Procedure |  | A | IFA | IFR | PR | [18 empty] | 3.1111 | 2
6 | VD-BH-00-PQ-000-IN-PS-1006 |  | Inspection Test Plan (ITP) |  | A | IFA | IFA | PS | [18 empty] | 7.7778 | 5
7 | VD-BH-00-PQ-000-IN-LI-1007 |  | Packing List |  | I | IFI | IFI | LI | [18 empty] | 4.6667 | 3
8 | VD-BH-00-PQ-000-IN-FI-1008 |  | Vendor data book index |  | A | IFA | IFR | FI | [18 empty] | 4.6667 | 3
9 | VD-BH-00-PQ-000-IN-FB-1009 |  | Vendor data book |  | A | IFA | IFR | FB | [18 empty] | 3.1111 | 2
Technical documents: | [27 empty] | 43
10 | VD-BH-00-PQ-000-IN-PI-1010 |  | Schematic Tubing and Instrumentation Diagram (P&ID) |  | A | IFA | IFI | PI | [18 empty] | 12.093 | 8
11 | VD-BH-00-PQ-000-IN-DW-1011 |  | General Arrangement And Dimensional Drawing Of Analyzer Package |  | A | IFA | IFA | DW | [18 empty] | 3.0233 | 2
12 | VD-BH-00-PQ-000-IN-DW-1012 |  | Sample Probe Drawing |  | A | IFA | IFA | DW | [18 empty] | 2.2674 | 1.5
13 | VD-BH-00-PQ-000-IN-BM-1013 |  | Mechanical Bill Of Material |  | A | IFA | IFR | BM | [18 empty] | 13.6047 | 9
14 | VD-BH-00-PQ-000-IN-LI-1014 |  | Utility and Power Consumption List |  | A | IFA | IFI | LI | [18 empty] | 13.6047 | 9
15 | VD-BH-00-PQ-000-IN-DT-1015 |  | Analyzer Data Sheet |  | A | IFA | IFA | DT | [18 empty] | 12.093 | 8
16 | VD-BH-00-PQ-000-IN-CN-1016 |  | Water Dew Point And Lag Time Calculation |  | A | IFA | IFR | CN
17 | VD-BH-00-PQ-000-IN-LI-1017 |  | Gas Cylinder List |  | A | IFA | IFI | LI | [18 empty] | 6.0465 | 4
18 | VD-BH-00-PQ-000-IN-LI-1018 |  | spare part list (commissioning and two years) |  | A | IFA | IFA | LI | [18 empty] | 2.2674 | 1.5
19 | VD-BH-00-PQ-000-IN-DG-1019 |  | Wiring Diagram |  | A | IFA | IFI | DG
20 | VD-BH-00-PQ-000-IN-LI-1020 |  | I/O List |  | A | IFA | IFI | LI
21 | VD-BH-00-PQ-000-IN-LI-1021 |  | Electrical Tie-in List |  | A | IFA | IFI | LI
22 | VD-BH-00-PQ-000-IN-BM-1022 |  | Electrical Bill Of Material |  | R | IFR | IFI | BM
23 | VD-BH-00-PQ-000-IN-CR-1023 |  | Certificates |  | I | IFI | IFI | CR